## Data
Requirements Traceability Matrix
Project Name: |  | TestKarts.com
| Project Manager | Manager Testkarts.com
Project Description: |  | Testing and Development project for the fresher and experience learner.
Requirements |  |  |  |  | Testing | [7 empty] | Defects
Req. ID | Requirements Description | Requirements Source | Requirement Type | WBS Deliverables | Test Case ID | Test Description | TEST | UAT | QA | PROD | PRE-PROD | NON-PROD | Defective | Defect ID | Defect Description | Req. Status
REQ001 | User registration functionality | Business Analyst | Functional | WBS-001 | TC001 | Verify user can successfully register an account | Pass | Pass | Pass | Pass | Fail |  | No |  |  | Complete
REQ001 | User registration functionality | Business Analyst | Functional | WBS-001 | TC002 | Verify error message is displayed for invalid inputs | N/A | Fail | Pass | Fail | N/A |  | Yes | DEF001 | Invalid email format | Complete
REQ001 | User registration functionality | Business Analyst | Functional | WBS-001 | TC003 | Verify user receives a confirmation email | Pass | N/A | Fail | N/A | Pass |  | Yes | DEF002 | Email not sent | In Progress
REQ002 | Login functionality | Product Owner | Functional | WBS-002 | TC004 | Verify user can log in with valid credentials | Fail | Pass | N/A | N/A | N/A |  | NO |  |  | In Progress
REQ002 | Login functionality | Product Owner | Functional | WBS-002 | TC005 | Verify error message is displayed for incorrect login | Fail | Fail | N/A | Pass | Fail |  | Yes | DEF003 | Incorrect username | Complete
REQ002 | Login functionality | Product Owner | Functional | WBS-002 | TC006 | Verify "Forgot Password" link redirects correctly | Fail | Fail | N/A | Pass | Pass |  | No |  |  | In Progress
REQ003 | Create new post | User Stories | Functional | WBS-003 | TC007 | Verify user can create a new post |  |  |  | N/A | N/A |  | No |  |  | Not Started
REQ003 | Create new post | User Stories | Functional | WBS-003 | TC008 | Verify error message is displayed for empty content | Pass | Pass | Pass | Fail | Fail |  | Yes | DEF004 | Empty post content | Complete
REQ003 | Create new post | User Stories | Functional | WBS-003 | TC009 | Verify post is displayed on the homepage |  |  |  | Pass | Pass |  | No |  |  | Partial Completion
For Reference Only |  |  |  | Note:- Requirements Traceability Matrix. Please remove it from the this template before using it.
Requirements Source |  |  | Click Here To Know More
WBS Deliverables |  |  | Click Here To Know More
Test |  |  | Click Here To Know More
UAT |  |  | Click Here To Know More
PROD |  |  | Click Here To Know More
Req. Status |  |  | Click Here To Know More

## Status
Req. Status | Sum of Req. ID
Not Started